|  |
| --- |
| **RHP 8 Behavioral Health and Primary Care Cohort****Team Charter** |
| Date: August 17, 2016 | Version: 2.1 |
|  |
| **Cohort Organizations** |
| Baylor Scott & White Medical Center - Llano | Lone Star Circle of Care |
| Bell County Public Health District | Seton Highland Lakes |
| Bluebonnet Trails Community Services | Texas A&M Health Science Center |
| Center for Life Resources | Williamson County Emergency Medical Services |
| Central Counties Services |  |
|  |
| **Purpose Statement** |
| *The Cohort will seek opportunities to increase communication and promote shared learning in RHP 8 with an overall focus on project sustainability.* |
|  |
| **Goals and Aims** |
| Goal 1 | Increase Communication Among Cohort Participants **Completed: September, 2014** |
| Aim 1 | Discuss Access to Care and Finding Resources **Completed: September, 2014** |
| Aim 2 | Develop an RHP 8 County-Based Resource Guide **Completed: September, 2014** |
| Goal 2 | Identify Early Barriers to Care and Develop Plan to Address Obstacles **Completed: March, 2015**  |
| ~~Aim 1~~ | ~~Share Continuing Medical Education (CME) Opportunities for Providers~~ **Removed: December, 2014** |
| Aim 2 | Identify Resources for Payment of Medication for Indigent Patients **Options Explored and Shared: March, 2015** |
| Aim 3 | Identify Resources for Transportation to Care **Options Explored and Shared: March, 2015** |
| Goal 3 | Increase information exchanged related to Waiver renewal in an effort to create a seamless transition into DY6 **Completed: August, 2016** |
| Aim 1 | Review HHSC transition proposal plan, and respond to plan by sharing list of questions and/or best practices with others in Cohort **Options Explored and Shared: June, 2016** |
| Aim 2 | Evaluate DSRIP projects using RHP 8 learning collaborative sustainability tool, and take action steps to address areas of improvement**Options Explored and Shared: August, 2016** |
| Goal 4 | ~~Understand potential Regional Performance Bonus Pools (RPBPs) measures and minimize financial risk~~ **Removed: August, 2016** |
| Aim 1 | ~~Understand expectations of HHSC and produce collective response and suggestions to HHSC to positively impact RPBPs in Region~~ **Removed: August, 2016** |
|  |

|  |
| --- |
| **Outputs** |
| Output 1 | Conduct two PDSAs to (1) identify Cohort Resource List and (2) drive Cohort Development/PlanningOutput of Goal 1/Aim 1**Completed: September, 2014** |
| Output 2 | Create and disseminate RHP 8 county-based resource guide used to identify services offered by both RHP 8 Providers and other community organizationsOutput of Goal 1/Aim 2**Completed: September, 2014** |
| Output 3 | ~~Create list of CMEs offered in this region; if RHP 8 stakeholders know of opportunities, send information to Anchor to disperse in monthly newsletter~~Output of Goal 2/Aim 1**Removed: December, 2014** |
| Output 4 | Create list of resources for payment of medication for indigent patientsOutput of Goal 2/Aim 2**Status: Resources and templates shared with members; comprehensive list not created, March 2015** |
| Output 5 | Create list of resources for transportation to careOutput of Goal 2/Aim 3**Status: Resources and templates shared with members; comprehensive list not created, March 2015** |
|  |
| **Communication Plan** |
| Provide update to stakeholders in region via the RHP 8 newsletter |
| Share brief recap of Cohort activities on RHP 8 conference calls with regional stakeholders as needed |
|  |
| **Meeting Log (Date and Focus of Meeting)** |
| **July 31, 2014** | Initial Cohort kick-off meeting |
| **August 14, 2014** | Cohort development meeting |
| **September 3, 2014** | Focus on Goal 1 – discuss aims and outputs related to Goal 1; e.g., draft template for county-based resource list |
| **September 24, 2014** | Finish working on county-based resource guide; re-cap activities of HHSC Summit; and discuss next-steps for Cohort |
| **December 3, 2014** | DY4 kick-off meeting – identify goals and aims to focus on during DY4 |
| **January 21, 2015** | Update on research done by Cohort members on medication management resources in the community; review of goals and aims for DY4 |
| **March 4, 2015** | Presentation provided by Faith Mission on Washington County Medication Assistance Program (MAP); members discussed information Beth McClary found via HOGG Foundation; Anchor team shared insights on how to address transportation gap in region without reinventing the wheel |
| **March 23, 2015** | Subgroup met to explore grant funding for access to emergency medication |
| **January 20, 2016** | DY5 Initial Cohort kick-off meeting |
| **February 18, 2016** | Draft Cohort Charter with goals and aims for DY5 |
| **April 7, 2016** | Review Cohort member’s experiences with internally reviewing Waiver transitional year materials, and address related questions/concerns/issues.  |
| **May 19, 2016** | Discuss Waiver renewal concerns/questions, and review project sustainability and evaluation tools.  |
| **June 16, 2016** | Review benefits of various program sustainability tools; review HHSC transition proposal plan; share concerns/questions with members in Cohort related to sustainability planning and reporting during DY6 |
| **August 17, 2016** | Discuss Waiver extension activities; providers share what they have learned about DSRIP projects through evaluation process and next steps they plan to take to improve projects |